## Main
Occur Date | Version | Issue | Date Fixed | Code Fixed | Remarks
2023-02-02 | 2 | Summary not opening after clicking |  | - await for summary to return before looping | While loop results in multiple instances of Summary
2023-02-02 | 1 | PRASS not showing after confirming on Summary page | 2023-02-02 | - Added SSL cert ignore to chrome option | Assume SSL cert handshake fail causing issues
2023-03-06 | 2 | Numbers not reflecting after clicking Okay on OddSize Page | 2023-03-07 | - Added mainloop for OddSize page to stop updating | MainPage update before OddSize due to concurrency
2023-03-07 | 2 | Keep having errors while scanning | 2023-03-07 | - Looped the camera calibration pin 5 times instead | Added loop to find best calibration pin image
2023-03-09 | 2 | Unable to detect lighter block colours | 2023-03-24 | - Nil | Installed Razer Software to tweak Cam Settings
2023-03-24 | 2 | Unable to detect lighter block colours part 2 | 2023-03-28 | - Nil | Anodized vacuum plate to blue
2023-03-29 | 2 | Unable to detect cali pin and process block with new anodized vacuum plate | 2023-04-03 | - Fixed Code to be able to retrieve Cali pin and block. - Cali pin still abit wonky where sometimes it wont retrieve. - Looped camera cali pin 10 times instead | Camera seems to have some internal color calibration